## Task Expense Statement
Task Expense Summary
Summary Tasks | Costs
Project Management | 38000.66
Design | 101120
Construction
Borlaug Building | 271400
Marquez Library | 271400
Salam Center | 407100 | A bar chart shows the expenses relative to each other. Do not include the sub-total or total in this chart.
Sen Building | 407100
Commissioning | 17600
Sub-total | 1513720.66
Contingency | 151279.34
Total | 1665000
Note on B12: AMC: This sub-total should be exactly the same as the project toal in the .mpp file.
Note on B13: AMC: The contingency has been adjusted to make the Total a round number. This is the only value that can be adjusted from the raw data to have the numbers sum correcty.

## Resource Expense Statement
Resource Expense Summary
Resource Group | Costs
Administration | 29520.66
Design | 127200
Equipment | 958000
Furniture | 199000
General Contractor | 200000 | A bar chart shows the expenses relative to each other. Do not include the sub-total or total in this chart.
Sub-total | 1513720.66
Contingency | 151279.34
Total | 1665000
Note on B9: AMC: This sub-total should be exactly the same as the sub-total in the Task Expense summary and the .mpp file.
Note on B11: AMC: When this is auto-summed, it should be the same total as the Task Expense Summary.

## Cash Flow Summary
Cash Flow Summary
Monthly
Tasks | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug
Project Management | 4100 | 17700 | 2097.45 | 2002.12 | 1906.78 | 2065.45 | 1985.45 | 6143.4
Design |  |  | 40016 | 59664 | 1440
Construction | [6 empty] | 1357000
Commissioning |  |  |  | 1120 | 1680 | 0 | 0 | 14800
Sub-total | 4100 | 17700 | 42113.45 | 62786.12 | 5026.78 | 2065.45 | 1358985.45 | 20943.4
Cumulative total | 4100 | 21800 | 63913.45 | 126699.57 | 131726.35 | 133791.8 | 1492777.25 | 1513720.65
Total with contingency | 1665000 | 1665000 | 1665000 | 1665000 | 1665000 | 1665000 | 1665000 | 1665000
Weekly
Tasks | 2009-01-04 | 2009-01-11 | 2009-01-18 | 2009-01-25 | 2009-02-01 | 2009-02-08 | 2009-02-15 | 2009-02-22 | 2009-03-01 | 2009-03-08 | 2009-03-15 | 2009-03-22 | 2009-03-29 | 2009-04-05 | 2009-04-12 | 2009-04-19 | 2009-04-26 | 2009-05-03 | 2009-05-10 | 2009-05-17 | 2009-05-24 | 2009-05-31 | 2009-06-07 | 2009-06-14 | 2009-06-21 | 2009-06-28 | 2009-07-05 | 2009-07-12 | 2009-07-19 | 2009-07-26 | 2009-08-02 | 2009-08-09 | 2009-08-16 | 2009-08-23
Project Management | 1025 | 1025 | 1025 | 1025 | 1025 | 1025 | 14625 | 1025 | 476.69 | 476.69 | 476.69 | 476.69 | 476.69 | 381.36 | 476.69 | 476.69 | 476.69 | 476.69 | 476.69 | 381.36 | 476.69 | 476.69 | 476.69 | 476.69 | 476.69 | 317.36 | 396.69 | 476.69 | 476.69 | 476.69 | 349.36 | 396.69 | 3397.36 | 2000
Monthly Tasks: Design | 7600 | 7600 | 13840 | 7840 | 7840 | 22080 | 22800 | 7200 | 3600 | 720
Monthly Tasks: Construction | [18 empty] | 496085.71 | 521966.67 | 316447.62 | 22500
Monthly Tasks: Commissioning | [7 empty] | 560 | 700 | 700 | 700 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5384.62 | 5230.77 | 4184.62
Sub-total | 1025 | 1025 | 1025 | 1025 | 1025 | 1025 | 14625 | 1025 | 8076.69 | 8076.69 | 14316.69 | 8316.69 | 8316.69 | 22461.36 | 23276.69 | 8236.69 | 4776.69 | 1896.69 | 1176.69 | 521.36 | 476.69 | 476.69 | 476.69 | 476.69 | 476.69 | 317.36 | 496482.4 | 522443.36 | 316924.31 | 22976.69 | 5733.98 | 5627.46 | 7581.98 | 2000
Cumulative total | 1025 | 2050 | 3075 | 4100 | 5125 | 6150 | 20775 | 21800 | 29876.69 | 37953.38 | 52270.07 | 60586.76 | 68903.45 | 91364.81 | 114641.5 | 122878.19 | 127654.88 | 129551.57 | 130728.26 | 131249.62 | 131726.31 | 132203 | 132679.69 | 133156.38 | 133633.07 | 133950.43 | 630432.83 | 1152876.19 | 1469800.5 | 1492777.19 | 1498511.17 | 1504138.63 | 1511720.61 | 1513720.61
Total with contingency | 1665000 | 1665000 | 1665000 | 1665000 | 1665000 | 1665000 | 1665000 | 1665000 | 1665000 | 1665000 | 1665000 | 1665000 | 1665000 | 1665000 | 1665000 | 1665000 | 1665000 | 1665000 | 1665000 | 1665000 | 1665000 | 1665000 | 1665000 | 1665000 | 1665000 | 1665000 | 1665000 | 1665000 | 1665000 | 1665000 | 1665000 | 1665000 | 1665000 | 1665000
A cumulative cost curve chart shows the expenses over time. This was made from the weekly timescale data, but the bottom axis was reformatted to only display the months. This keeps the information consistent, but gives more data points for a more accurate line.
Note on A2: AMC: A monthly or quarterly table is an appropriate timescale to keep the table readable in the summary plan.
Note on A12: AMC: A smaller timescale, like weekly, should be used for the chart so that there are more data points per reporting period.
Note on I9: AMC: This should be the same as the sub-total in the Resource and Task Expense Summaries and the .mpp file.