| Emanon College Lab Build | Status Date: 26 June 2009 Author: Rebecca Brown |
| --- | --- |

| ( - Baseline milestone ( - Actual or expected future milestone |  |
| --- | --- |

## Overall Project Performance

|  | Status | Comments |
| --- | --- | --- |
| Scope |  | Project has 50% of work complete but only 9% of value complete. Most of the value is in the lab equipment. Design phase work is complete. Operations manuals have not commenced as planned, but will be completed within the next reporting period. Lab build work will be conducted in next reporting period. |
| Schedule |  | Construction documents and Designs were both completed two months behind schedule, but in time for construction. Operations manual completion has been pushed out to late July, but this is not a critical milestone yet. Lab construction is still expected to start as planned. The schedule is progressing within acceptable variance. |
| Budget |  | The project has spent $146k (10%) out of the $1.5M budget. Work performed to date: $130k value ($16k over budget). Receiving $0.89 of value for every $1 spent, but most remaining costs are fixed. Estimate at Completion: $1.5M based on fixed costs. |
| Resources |  | Finance manager was released from the project due to poor performance. Finance Director has replaced Finance Manager. |
| Risks |  | No major risk occurrences during reporting period. Risks during construction are low exposure. |
| Changes |  | Sponsor requested that project be completed by August 15, 2009. Minimal rescheduling was required to accommodate request. |

| Status Legend |  Controlled |  Caution |  Critical |
| --- | --- | --- | --- |
| Scope | Deliverables and work are acceptable in current state. | Deliverable or work status is uncertain or moderate rework is required to be acceptable. | Deliverable is not viable or significant rework is required. |
| Schedule | Schedule Performance is within 5% of planned rate. | Schedule Performance is >5% and <10% of planned rate. | Schedule Performance is >10% of planned rate or critical milestone will be missed by unacceptable amount. |
| Budget | Cost Variance % is within 5% of planned amount. | Cost Variance % is >5% and <10% of planned amount. | Cost Variance % is >10% of planned amount or EAC is greater than BAC + contingency. |
| Resources | Resources are available and being utilized as planned. | Resources are being under or over-utilized by <10% of planned amount. | Resources are unavailable or are being utilized >10% of planned amount |
| Risks | No major risk occurrences. | Minor risk occurrences affecting project objectives. | Major risk occurrence has affected project objective and contingency plan has been activated. |
| Changes | No changes requested or required, or any changes initiated affect the project <10%. | Minor changes requested or required affecting the project between 10% and 15%. | Major project changes requested or required affecting the project >15%. |

# Comments

Name the project that is being reported.  Keep this report to 1 page.

Always include the status date from the .mpp file in plain language.

Format the milestone chart to display only the relevant milestones and include the dates.

Include a legend for the reader.

Copy these symbols from the Status Legend based on the status of each category.

Use bullet points to keep this succinct.

The project manager must determine what the most appropriate representation of the % complete of the project is.

Only report work that was during the monthly reporting period.  There is no reason to report achievements in previous reporting periods, because these would have been reported already.

The milestones are stated in plain language.

It is also possible to state the SPI in plain language in this section.

This section should be stated in plain language and should be succinct.

AC, % Spent and BAC in one bullet.

EV and CV in one bullet

CPI in one bullet to justify the status.

EAC should be appropriate.

Not all resource information needs to be reported.  Use discretion when reporting.

Only report major risk occurrences as necessary.

Only report major changes.