## Project Report
Project Report | [5 empty] | Status Date:
Project: | [7 empty] | l Critical
Author: | [7 empty] | t Concern
Timeline | [7 empty] | (t Baseline; t Actual; t Forecast)
Scope Performance | [7 empty] | Expected Completion
Deliverable or Phase |  |  |  |  | % Complete
| Overall Project |  |  |  | #NAME? |  | 0%
#NAME?
#NAME?
#NAME?
#NAME?
#NAME?
#NAME?
Budget Performance |  |  |  | Schedule Performance
| Measure |  | (¦ Actual; ▮ Acceptable) |  | Measure |  |  | (¦ Actual; ▮ Acceptable)
| Work Planned to Date | 0 | #NAME? | #DIV/0! | Progress Rate |  | #DIV/0! | #NAME?
| Work Finished to Date | 0 | #NAME? |  |  |  |  | Days Until/ Past Due
| Amount Spent to Date | 0 | #NAME? |  | Milestone |  | Due Date
#DIV/0! | Budget Status | 0
#DIV/0! | Value Per $1.00 Paid | #DIV/0! | #NAME?
| Planned Total Cost | 0
| Forecast Total Cost | 0
Issues |  |  |  | Actions to Address
Major Activities for Next Period

## Report Data
Earned Value Data | PV | EV | AC | BAC | % Work Complete | % Complete | Physical % Complete
Base values copied from MSP
PV | 0
EV | 0
AC | 0
BAC | 0
% Work Complete | 0%
% Duration Complete | 0%
Physical % Complete | 0%
Planned % Complete | #DIV/0!
EV % Complete | #DIV/0!
% Spent | #DIV/0!
CV | 0
CV% | #DIV/0!
SV | 0
SV% | #DIV/0!
CPI | #DIV/0!
SPI | #DIV/0!
EAC = BAC/CPI | #DIV/0!
EAC = AC + BAC - EV | 0
EAC = AC + [(BAC-EV)/(CPIxSPI)] | #DIV/0!
VAC | #DIV/0!
ETC | #DIV/0!
TCPI | #DIV/0!
Cost Variance Over Time | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug
CV from Task Usage
Milestones | #DIV/0! Feb: Due Date; #DIV/0! Mar: Past Due

## Sample Project Report
Project Report | [5 empty] | Status Date: |  | 2009-06-26
Project: |  | Emanon College Lab Build Project | [5 empty] | l Critical
Author: |  | Rebecca Brown | [5 empty] | t Concern
Timeline | [7 empty] | (t Baseline; t Actual; t Forecast)
Scope Performance | [7 empty] | Expected Completion
Deliverable or Phase |  |  |  |  | % Complete
| Overall Project |  |  |  | #NAME? |  | 50% | 2009-08-15
| Lab designs |  |  |  | #NAME? |  | 100% | 2009-06-26
| Borlaug Labs |  |  |  | #NAME? |  | 0% | 2009-07-22
| Marquez Labs |  |  |  | #NAME? |  | 0% | 2009-07-22
| Salam Labs |  |  |  | #NAME? |  | 0% | 2009-08-04
| Sen Labs |  |  |  | #NAME? |  | 0% | 2009-07-31
| Operations manuals |  |  |  | #NAME? |  | 0% | 2009-07-17
Budget Performance |  |  |  | Schedule Performance
| Measure |  | (¦ Actual; ▮ Acceptable) |  | Measure |  |  | (¦ Actual; ▮ Acceptable)
| Work Planned to Date | 500000 | #NAME? | n | Progress Rate |  | 98% | #NAME?
| Work Finished to Date | 490000 | #NAME? |  |  |  |  | Days Until/ Past Due
| Amount Spent to Date | 550000 | #NAME? |  | Milestone |  | Due Date
t | Budget Status | -60000 | Over budget |  | Designs complete |  | 2009-05-04 17:00 | 0
l | Value Per $1.00 Paid | 0.89091 | #NAME? |  | Lab construction started |  | 2009-07-06 08:00 | 9.63
| Planned Total Cost | 1513800 |  | t | Ops manuals complete |  | 2009-05-19 17:00 | -38
| Forecast Total Cost | 1573800 |  |  | Labs complete |  | 2009-08-07 17:00 | 42
Issues |  |  |  | Actions to Address
| Finance manager has been removed |  |  | Replaced with Finance Director
t | Deadline changed to August 15, 2009 |  |  | Adjusted remaining tasks to meet deadline
| Construction team at max. capacity |  |  | Started looking for additional resources
Major Activities for Next Period
Construction of first 8 labs
Production of operations manuals
32%
32%
32%
36%
32%
33%

## Sample Project Data
Earned Value Data | PV | EV | AC | BAC | % Work Complete | % Complete | Physical % Complete
Base values copied from MSP | 500000 | 490000 | 550000 | 1513800 | 50% | 74% | 0%
PV | 500000
EV | 490000
AC | 550000
BAC | 1513800
% Work Complete | 50%
% Duration Complete | 74%
Physical % Complete | 0%
Planned % Complete | 33.03%
EV % Complete | 32.37%
% Spent | 36.33%
CV | -60000
CV% | -12.24%
SV | -10000
SV% | -2.041%
CPI | 0.89091
SPI | 0.98
EAC = BAC/CPI | 1699163.2653
EAC = AC + BAC - EV | 1573800
EAC = AC + [(BAC-EV)/(CPIxSPI)] | 1722615.5768
VAC | -185363.2653
ETC | 1149163.2653
TCPI | 1.0623
Cost Variance Over Time | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug
CV from Task Usage | -508 | -1016 | -2272 | 18202.51 | -4154.29 | -16104.34
Milestones | 1.0623 Feb: Due Date; 1.0623 Mar: Past Due
Designs complete | 1.0623 Feb: 2009-05-04 17:00; 1.0623 Mar: 0
Lab construction started | 1.0623 Feb: 2009-07-06 08:00; 1.0623 Mar: 9.63
Ops manuals complete | 1.0623 Feb: 2009-05-19 17:00; 1.0623 Mar: -38
Labs complete | 1.0623 Feb: 2009-08-07 17:00; 1.0623 Mar: 42

## Dropdowns
Exposure | Status | Priority | Departments
l | Controlled | Vital | Operations
t | Hindered | Urgent | Human Resources
n | Blocked | Normal | Special Projects
Administration
Marketing
Sample Row