## Task Expense Statement
Task Expense Summary
Summary Tasks | Baseline | Actual | Variance
Project Management | 38080 | 35761.24 | -2318.76
Design | 101120 | 117960 | 16840
Construction
Borlaug Building | 271400 | 271400 | 0
Marquez Library | 271400 | 271400 | 0
Salam Center | 407100 | 407100 | 0
Sen Building | 407100 | 407100 | 0
Commissioning | 17600 | 18000 | 400
Sub-total | 1513800 | 1528721.24 | 14921.24
Contingency | 151200 | 14921.24
Total | 1665000

## Resource Expense Statement
Resource Expense Summary
Resource Group | Baseline | Actual | Variance
Administration | 29600 | 27321.24 | -2278.76
Design | 127200 | 144400 | 17200
Equipment | 958000 | 958000 | 0
Furniture | 199000 | 199000 | 0
General Contractor | 200000 | 200000 | 0
Sub-total | 1513800 | 1528721.24 | 14921.24
Contingency | 151200 | 14921.24
Total | 1665000

## Cash Flow Summary
Cash Flow Summary
Actual Monthly
Tasks | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug
Project Management | 3788 | 17388 | 1288.07 | 2002.12 | 1906.78 | 1684.89 | 2065.64 | 5637.75
Design |  |  | 14912 | 26061.49 | 56860.79 | 20125.71
Construction | [6 empty] | 1353000 | 4000
Commissioning | [5 empty] | 160 | 15327.18 | 2512.82
Sub-total | 3788 | 17388 | 16200.07 | 28063.61 | 58767.57 | 21970.6 | 1370392.82 | 12150.57
Cumulative total | 3788 | 21176 | 37376.07 | 65439.68 | 124207.25 | 146177.85 | 1516570.67 | 1528721.24
Total with contingency | 1665000 | 1665000 | 1665000 | 1665000 | 1665000 | 1665000 | 1665000 | 1665000
Weekly
Tasks | 2009-01-04 | 2009-01-11 | 2009-01-18 | 2009-01-25 | 2009-02-01 | 2009-02-08 | 2009-02-15 | 2009-02-22 | 2009-03-01 | 2009-03-08 | 2009-03-15 | 2009-03-22 | 2009-03-29 | 2009-04-05 | 2009-04-12 | 2009-04-19 | 2009-04-26 | 2009-05-03 | 2009-05-10 | 2009-05-17 | 2009-05-24 | 2009-05-31 | 2009-06-07 | 2009-06-14 | 2009-06-21 | 2009-06-28 | 2009-07-05 | 2009-07-12 | 2009-07-19 | 2009-07-26 | 2009-08-02 | 2009-08-09 | 2009-08-16 | 2009-08-23
Project Management | 1025 | 1025 | 1025 | 1025 | 1025 | 1025 | 14625 | 1025 | 476.69 | 476.69 | 476.69 | 476.69 | 476.69 | 381.36 | 476.69 | 476.69 | 476.69 | 476.69 | 476.69 | 381.36 | 476.69 | 476.69 | 476.69 | 476.69 | 476.69 | 317.36 | 396.69 | 476.69 | 476.69 | 476.69 | 349.36 | 396.69 | 396.69 | 5080
Actual Monthly Tasks: Design | 7600 | 7600 | 13840 | 7840 | 7840 | 22080 | 22800 | 7200 | 3600 | 720
Actual Monthly Tasks: Construction | [18 empty] | 557966.67 | 520442.86 | 48190.48 | 226400 | 4000
Actual Monthly Tasks: Commissioning | [7 empty] | 560 | 700 | 700 | 700 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4338.46 | 5230.77 | 5230.77
Sub-total | 1025 | 1025 | 1025 | 1025 | 1025 | 1025 | 14625 | 1025 | 8076.69 | 8076.69 | 14316.69 | 8316.69 | 8316.69 | 22461.36 | 23276.69 | 8236.69 | 4776.69 | 1896.69 | 1176.69 | 521.36 | 476.69 | 476.69 | 476.69 | 476.69 | 476.69 | 317.36 | 558363.36 | 520919.55 | 48667.17 | 226876.69 | 8687.82 | 5627.46 | 5627.46 | 5080
Cumulative total | 1025 | 2050 | 3075 | 4100 | 5125 | 6150 | 20775 | 21800 | 29876.69 | 37953.38 | 52270.07 | 60586.76 | 68903.45 | 91364.81 | 114641.5 | 122878.19 | 127654.88 | 129551.57 | 130728.26 | 131249.62 | 131726.31 | 132203 | 132679.69 | 133156.38 | 133633.07 | 133950.43 | 692313.79 | 1213233.34 | 1261900.51 | 1488777.2 | 1497465.02 | 1503092.48 | 1508719.94 | 1513799.94
Total with contingency | 1665000 | 1665000 | 1665000 | 1665000 | 1665000 | 1665000 | 1665000 | 1665000 | 1665000 | 1665000 | 1665000 | 1665000 | 1665000 | 1665000 | 1665000 | 1665000 | 1665000 | 1665000 | 1665000 | 1665000 | 1665000 | 1665000 | 1665000 | 1665000 | 1665000 | 1665000 | 1665000 | 1665000 | 1665000 | 1665000 | 1665000 | 1665000 | 1665000 | 1665000
Earned Value | 820 | 1640 | 2460 | 3280 | 4100 | 4920 | 5740 | 20160 | 20980 | 21800 | 27437.75 | 33075.49 | 38713.26 | 49959.46 | 59217.21 | 67274.98 | 89391.39 | 110814.49 | 116785.57 | 118682.44 | 121053.54 | 123980.49 | 127278.07 | 129575.63 | 131186.61 | 131985.58 | 691041.85 | 1214666.61 | 1269157.98 | 1501782.53 | 1508720 | 1513800
Actual Cost | 947 | 1894 | 2841 | 3788 | 4735 | 5682 | 20229 | 21176 | 21248 | 21320 | 29236.69 | 37153.39 | 37710.08 | 45751.94 | 50980.27 | 56666.88 | 67956.26 | 83659.19 | 100042.11 | 110933.28 | 124207.24 | 133681.45 | 139533.38 | 143323.56 | 145882.98 | 146494.73 | 705278.58 | 1229155.38 | 1283918.26 | 1516570.67 | 1523481.24 | 1528721.24
This chart will automatically populate when you insert the BCWP and ACWP data into the weekly table above.
Note on A2: AMC: Notice that this table displays Actual Costs rather than Baseline Costs.
Note on A12: AMC: This is the data that has been used since the start of the project, simply inserting the new EV and AC information each reporting period.
Note on A21: AMC: This data is copied from the Task Usage view of the .mpp file as BCWP. It is plotted in the chart as "Work Performed" for plain language.
Note on A22: AMC: This data is copied from the Task Usage view of the .mpp file as ACWP. The text in these cells have been coloured similarly to the chart.