## Sheet1
Lab Build Project - Sample
Project approved
Project Management
Plan project
Monitor & control project
Close project
Design
Analyse lab requirements
Develop furniture specs
Develop equipment specs
Design lab interiors
Design lab interiors - Borlaug
Design lab interiors - Marquez
Design lab interiors - Salam
Design lab interiors - Sen
Develop construction documents
Develop architectural specs
Develop structural specs
Develop electrical specs
Develop mechanical specs
Develop communications/data specs
Develop security specs
Construction
Sen Building
Build Lab E210
Build Lab E211
Build Lab E212
Marquez Library
Build Lab L316
Build Lab L315
Borlaug Building
Build Lab B108
Build Lab B107
Salam Center
Build Lab S324
Build Lab S325
Build Lab S326
Commissioning
Test all labs
Produce as-built documents for all labs
Produce operations and maintenance manuals
Project complete