## Blank
Dashboard Report
Department |  | Report Date
Author
Objectives |  | Performance | Status
Accomplishments
Initiative | Major Milestone | Due Date | Days Until/ Past Due
0
0
0
0
0
Concerns/Potential Issues |  |  | Exposure
Actions/Steps to Address Concerns/Potential Issues |  |  | Priority
Planned Activities for Next Period

## Objectives
Objective 1 Performance
Measure | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12
Planned
Actual
Variance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Variance % | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
% Complete
Relevant Target
Objective 2 Performance
Measure
Current | 0
Target | 0
Variance | 0
Variance % | #DIV/0!
% Complete | 0%
Maximum | 0

## Sample
Dashboard Report
Department | Operations |  | Report Date | 2022-08-31
Author | Jane Doe
Objectives |  |  | Performance | Status
Develop 10 new programs |  |  | #NAME? | #NAME?
Reduce service complaints by 25% |  |  | #NAME? | #NAME?
Improve awareness levels by 50% |  |  | #NAME? | #NAME?
Increase program enrollment by 25% |  |  | #NAME? | #NAME?
Achieve satisfaction rating of 4/5 |  |  | #NAME? | #NAME?
Improve satisfaction levels by 10% |  |  | #NAME? | #NAME?
Provide 24 hours PD to ea. employee |  |  | #NAME? | #NAME?
Ensure all IT systems are <4 y.o. |  |  |  | #NAME?
Accomplishments
Started developing new programs based on community input
Started implementing improvements to 3 services based on customer and employee feedback
Promotional campaigns started
Started employee PD analysis and information gathering
IT audit data requirements identified
Initiative |  | Major Milestone | Due Date | Days Until/ Past Due
New programs |  | Implemented 5 new programs | 2022-10-31 | 61
New services |  | Service project complete | 2022-09-30 | 30
Promotional campaign |  | Complete promotional campaign | 2022-08-31 | 0
Satisfaction survey |  | Survey data received | 2022-08-15 | -16
Employee PD program |  | PD program designed | 2022-08-21 | -10
Concerns/Potential Issues |  |  |  | Exposure
- Labour dispute possible next month |  |  |  | Critical | Critical
- Overallocation of staff in upcoming weeks |  |  |  | Caution | Caution
- Satisfaction survey initiative cost variance is approaching unacceptable level |  |  |  | Moderate | Moderate
Actions/Steps to Address Concerns/Potential Issues |  |  |  | Priority
- Plan to complete critical activities necessary for continuity before possible work action |  |  |  | Normal | Vital
- Renegotiate schedules and scope of concurrent projects to level staff utilization |  |  |  | Vital | Vital
- Investigate potential future cost savings on survey and improvements to recover variance |  |  |  | Urgent | Urgent
Planned Activities for Next Period
- Initiate IT audit
- Review new services and satisfaction objective achievement
- Start quarterly staff reviews
- Start delivering employee PD programs
5%
10%
70%
80%
70%
80%
75%
30%

## Sample Objective Data
Develop 10 new programs
# Programs Dev.
# Planned to date | 4
# Developed to date | 3
% Complete | 30%
Relevant Target | 10
Reduce service complaints by 25%
# Complaints
Orig. Complaints/mo. | 16
Current # Complaints | 15
Variance | 1
Variance % | 6.25%
% Complete | 75%
Relevant Target | 12
Improve awareness level by 50%
Survey Awareness Average
Survey result | 40%
Current result | 58%
Increase | 45%
Target Increase | 50%
% Complete | 80%
Increase program enrollment level by 25%
Enrollment Levels | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar
Previous year | 150 | 120 | 110 | 60 | 50 | 215 | 200 | 185 | 78 | 160 | 150 | 143
Target | 225 | 180 | 165 | 90 | 75 | 322.5 | 300 | 277.5 | 117 | 240 | 225 | 214.5
Actual | Apr: 140; May: 125; Jun: 130; Jul: 75; Aug: 70
Variance | Apr: -85; May: -55; Jun: -35; Jul: -15; Aug: -5
Variance % | -56.67% | -45.83% | -31.82% | -25% | -10% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
% Complete | Apr: 80%
Achieve satisfaction rating of 4/5
Overall Satisfaction
Current | Apr: 3.8
Target | Apr: 4
Variance | Apr: -0.2
Variance % | Apr: -5%
% Complete | Apr: 70%
Maximum | Apr: 5
Improve satisfaction levels by 10%
Overall Satisfaction
Survey result | Apr: 3.8
Current result | Apr: 4
Increase | Apr: 5.263%
Target Increase | Apr: 10%
% Complete | Apr: 70%
Maximum | Apr: 5
Provide 24h PD to each employee
Avg. hrs/emp.
Target Average | Apr: 24
Current Average | Apr: 2
% of Target | Apr: 8.333%
% Complete | Apr: 10%
Maximum | Apr: 32
Ensure all IT systems are <4 y.o.
Value of outdated systems
Target | Apr: 0
Actual | Apr: 0
Total value systems | Apr: 0
Variance % | Apr: 0
% Complete | bar: Apr

## Dropdowns
Exposure | Status | Priority | Departments
Critical | Controlled | Vital | Operations
Caution | Hindered | Urgent | Human Resources
Moderate | Blocked | Normal | Special Projects
Administration
Marketing
Sample Row