## Risk Register
Risk Register |  |  |  | Project Manager: | Rebecca Brown
| Project Name: | Lab Build |  | Revision Date: | 2009-02-28
|  | Risk Identification |  |  |  |  | Qualitative Analysis |  |  | Quantitative Analysis |  |  | Response Development |  |  | Monitoring & Control
Priority | ID # | Category | Type | Risk Triggers | Risk Event (Threat or Opportunity) | Risk Symptoms | Probability Low - High 1-2-3-4-5 | Impact Low - High 1-2-4-8-16 | Score Prob x Imp | Probability % | Quantified Impact | Exposure | Response Type | Response Strategy | Owner Responsible | Monitoring Action | Monitoring Timing | Status
|  |  | Objective | [9 empty] | Avoid
|  |  | Deliverable | [9 empty] | Transfer
|  |  | Work | [9 empty] | Mitigate
|  |  | Resource | [9 empty] | Exploit
|  |  | Schedule | [9 empty] | Share
|  |  | Budget | [9 empty] | Enhance
|  |  | Stakeholder | [9 empty] | Accept (Active)
|  |  | Communication | [9 empty] | Accept (Passive)
External
1 | 6 | Financial | Budget | Legislative budget cuts to publicly funded education institutions. | Project funding is reduced by more than 25% during project planning. | Notification of budget cut from sponsor. | 2 | 16 | 32 | 10% | 750000 | 75000 | Mitigate | Establish full project funding approval as early as possible, with commitment to contracts as top priority. | Sponsor | Assign project cost centre with established budget based on charter budget estimates. | As early as possible
2 | 4 | Project Mgmt | Resource | Higher priority projects are approved during the planning or execution of this project, requiring the PM. | Project manager is reassigned away from the project during execution. | Formal reassignent and announcement of project manager change | 2 | 8 | 16 | NA | NA | NA | Mitigate | Assign backup project manager to project, and provide periodic project briefs to backup PM. | PM | Provide semi-monthly project briefings to backup PM. Review project portfolio monthly to adjust probability as necessary. | Monthly Semi-monthly
3 | 1 | Technical | Work | Facilities group are not notified of building schedule with sufficient time to remove equipment. | Rooms are not emptied of existing lab equipment or furniture before new lab construction is scheduled to begin. | Construction contractor notification of equipment in room. | 2 | 4 | 8 | NA | NA | NA | Mitigate | Notify all facilities staff of construction schedule for existing rooms as soon as known, two weeks before construction begins, and one week before construction begins. | Facilities Manager | Review of the status of schedule dependencies on room construction activities at monthly meetings (Agenda item) | Monthly Two-weeks before demolition starts One week before demolition starts
4 | 5 | Union | Stakeholder | Poor communication of responsibilities of GC to union representatives and employees. | Bargaining unit employees block access to contractor to complete room renovations | Contact from GC regarding blockade. | 1 | 4 | 4 | NA | NA | NA | Accept (Active) | Discuss situation with union representatives prior to and during contract work. | PM | Notify employees of GC work schedule and work being performed at least one week prior to GC arrival. | One week before GC scheduled to start work
5 | 3 | Technological | Deliverable | Incorrectly configured wireless hardware. | Wireless network equipment does not recognize new devices as required | During final testing, laptops cannot access the correct wireless network. | 2 | 2 | 4 | NA | NA | NA | Accept (Active) | Reconfigure wireless equipment and include reconfiguration time estimate in plan. | PM & IS | Test equipment. | Upon receipt of wireless equipment.
6 | 2 | Sequential | Schedule | Shipping/receiving not notified of equipment and furniture delivery schedule | New equipment/furniture arrives before space has been cleared for it. | Notification of delivery of equipment ahead of schedule. Designated storage spaces not cleared prior to expected delivery dates. | 4 | 1 | 4 | NA | NA | NA | Accept (Passive) | Monitor | Facilities Manager | Monitor space availability and delivery schedules with Shipping/Receiving dept. | According to shipping schedule
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Note on H3: AMC: Once the qualitative analysis has been completed, sort the risks by priority.
Note on K3: AMC : Should only be conducted on risks as required by risk tolerances.
Note on N3: AMC: Risk responses should be proactive to reduce, transfer or eliminate the threats as much as possible. Proactive means that the strategy should be implemented before the risk occurs.
Note on A4: AMC : Priority number assigned by the project development team to the risk.
Note on B4: AMC : Unique identifier for this risk assigned by the team for tracking purposes. Valid entries are alpha, numeric or combination of both.
Note on C4: AMC : Broadly-defined area of risk for organization. Usually categories are created as part of risk identification and organization of the risk list.
Note on D4: AMC : Major impact area for the risk.
Note on E4: AMC : Detailed description of the situation, condition, event or circumstance that could precipitate the risk.
Note on F4: AMC : Specific definition of the risk event that could occur on the project.
Note on G4: AMC : Indicator that the risk has occured. Used to determine when to implement the risk response strategy.
Note on H4: AMC : Qualitative assessment of the likelihood of the risk occurring.
Note on I4: AMC : The severity of the risk's effect on the project objectives.
Note on J4: AMC : Automatically calculated. Product of the qualitative probability and impact. Thresholds and required actions are based on the selected risk matrix defined in the risk management plan and included as a worksheet in this document. After qualification, risks should be sorted and prioritized by this score.
Note on K4: AMC : Quantified assessment of the percentage likelihood of the risk occurring.
Note on L4: AMC : Quantified assessment of the impact on the project objectives in measurable terms (e.g. dollars, days, quality, etc.)
Note on M4: AMC : Should be calculated product of quantified probability and impact values.
Note on N4: AMC : The response type that is most likely to be effective for each risk. Valid entries are Avoidance, Transference, Mitigation, Exploit, Share, Enhance, Active acceptance or Passive acceptance.
Note on O4: AMC : Detailed response action to be taken to address the risk.
Note on P4: AMC : Name(s) or role(s) of person or people responsible for the risk.
Note on Q4: AMC : Action(s) required to monitor and control the risks and/or implement any contingency plans.
Note on R4: AMC : Frequency or timing of monitoring and controlling actions.
Note on S4: AMC : Status of the risk and/or response, including active, dormant or retired status and detailed explanation.
Note on D19: AMC: These fields are used for organizing and helping identify more risks. Most risks will have multiple impacts, so could be more than one type. Identify the type that helps organize most effectively.
Note on E19: AMC: It is possible to have several risk events from a single trigger situation. If more risk events can occur from a trigger, use more than one row in the table.
Note on F19: AMC: The risk is stated with a threshold to define the point at which the event has occurred.
Note on G19: AMC: The symptom is often a clearly understood notification.
Note on I19: AMC: This is using a non-linear scale to emphasize impact. This has been changed from the default in the template to demonstrate a different scale. A very high impact would normally be considered a project-ending risk.
Note on N19: AMC: This will reduce the risk, but not completely eliminate it.
Note on O19: AMC: If more than one response strategy is applied, use more than one row.
Note on F20: AMC: It is very common for key project team members to leave a project. Try to be specific about which person is so key to the project that their exit would be a risk event.

## Sample Categories
Sample Categories
Administrative
Archeological
Commercial
Construction
Contractual
Criminal
Cultural
Currency
Economic
Environmental
Ethical
Financial
Geographical
Geological
Health
Informational
Legal
Market
Natural
Organizational
Performance
Political
Procedural
Project Management
Quality
Regional
Regulatory
Right-of-way
Safety
Seasonal
Security
Sequential
Shipping
Technical
Technological
Time zone
Transitional
Transportation
Union
Zoning
Note on A1: AMC: These sample categories are only used to help the stakeholders identify more risk events that could occur on the project.

## Risk Matrix
Risk Matrix (Linear)
Probability | 5 | 5 | 10 | 15 | 20 | 25 | >14 | High Risk - Requires quantification and response development
| 4 | 4 | 8 | 12 | 16 | 20 | 5-14 | Moderate Risk - Requires response development, but not quantification
| 3 | 3 | 6 | 9 | 12 | 15 | <5 | Low Risk - Requires active or passive acceptance
| 2 | 2 | 4 | 6 | 8 | 10
| 1 | 1 | 2 | 3 | 4 | 5
|  | 1 | 2 | 3 | 4 | 5
Impact
Risk Matrix (Non-linear)
Probability | 5 | 5 | 10 | 20 | 40 | 80 | >16 | High Risk - Requires quantification and response development
| 4 | 4 | 8 | 16 | 32 | 64 | 8-16 | Moderate Risk - Requires response development, but not quantification
| 3 | 3 | 6 | 12 | 24 | 48 | <8 | Low Risk - Requires active or passive acceptance
| 2 | 2 | 4 | 8 | 16 | 32
| 1 | 1 | 2 | 4 | 8 | 16
|  | 1 | 2 | 4 | 8 | 16
Impact