## Worksheet
Earned Value Calculation Table
BCWS | BCWP | ACWP | BAC | % Work Complete | % Complete
133633.124 | 129778.6366 | 145882.9752 | 1513800 | 50% | 74%
PV | 133633.124 |  | The project planned to have completed $133,633 worth of work by the status date.
EV | 129778.6366 |  | The project has completed $129,779 worth of work by the status date.
AC | 145882.9752 |  | The project has spent $145,883 as of the status date.
BAC | 1513800 |  | The total budget of the project is $1,513,800.
% Work Complete | 50% |  | The project has completed 50% of its total work.
% Duration Complete | 74% |  | The project has completed 74% of its total duration.
% Value Complete | 8.573% |  | The project has completed 9% of its value.
% Spent | 9.637% |  | The project has spent 10% of the budget.
CV | -16104.3386 | t | The project is $16,104 over budget.
SV | -3854.4873 | n | The project is $3,854 behind schedule.
CPI | 0.88961 | l | The project is receiving $0.89 worth of value for every dollar spent.
SPI | 0.97116 | n | The project is progressing 3% slower than planned.
EAC1 | 1529904.3386 | n | If the trend is not expected to continue, the project is forecast to cost $1,529,904.
EAC2 | 1701648.6965 | l | If the trend continues, the project is forecast to cost $1,701,649.
EAC3 | 1747855.6795 | l | If the cost and schedule trends continue, the project is forecast to cost $1,747,856.
VAC1 | -16104.3386 | n | If the trend is not expected to continue, the project is forecast to be $16,104 over budget.
VAC2 | -187848.6965 | l | If the trend is expected to continue, the project is forecast to be $187,849 over budget.
VAC3 | -234055.6795 | l | If the cost and schedule trends are expected to continue, the project is forecast to be $234,056 over budget.
ETC1 | 1384021.3634 | n | If the trend is not expected to continue, $1,384,021 will be required to complete the project.
ETC2 | 1555765.7213 | l | If the trend is expected to continue, $1,555,766 will be required to complete the project.
ETC3 | 1601972.7043 | l | If the cost and schedule trends are expected to continue, $1,601,973 will be required to complete the project.
TCPI | 1.0118 |  | To complete the project within the original budget, $1.01 worth of value must be received for every dollar spent for the remainder of the project.
Milestones | Due Date | Finish Variance | #days
Designs complete | 2009-05-04 17:00 | 38 days | 38 | Designs complete is 38 days behind schedule.
Lab construction started | 2009-07-06 08:00 | 0 days | 0 | Lab construction started is exactly on schedule.
Operations manuals complete | 2009-05-19 17:00 | 42 days | 42 | Operations manuals complete is 42 days behind schedule.
Note on F2: AMC: These values were copied from the .mpp file.
Note on C29: AMC: These values were copied from the tracked .mpp file.

## Sample
Earned Value Calculation Table
BCWS | BCWP | ACWP | BAC | % Work Complete | % Complete
325000 | 375000 | 350000 | 500000 | 60% | 83.33%
PV | 325000 |  | The project planned to have completed $325,000 worth of work by the status date.
EV | 375000 |  | The project has completed $375,000 worth of work by the status date.
AC | 350000 |  | The project has spent $350,000 as of the status date.
BAC | 500000 |  | The total budget of the project is $500,000.
% Work Complete | 60% |  | The project has completed 60% of its total work.
% Duration Complete | 83.33% |  | The project has completed 83% of its total duration.
% Complete | 75% |  | The project has completed 75% of its value.
% Spent | 70% |  | The project has spent 70% of the budget.
CV | 25000 | n | The project is $25,000 under budget.
SV | 50000 | n | The project is $50,000 ahead of schedule.
CPI | 1.0714 | n | The project is receiving $1.07 worth of value for every dollar spent.
SPI | 1.1538 | n | The project is progressing 15% faster than planned.
EAC1 | 475000 | n | If the trend is not expected to continue, the project is forecast to cost $475,000.
EAC2 | 466666.6667 | n | If the trend continues, the project is forecast to cost $466,667.
EAC3 | 451111.1111 | n | If the cost and schedule trends continue, the project is forecast to cost $451,111.
VAC1 | 25000 | n | If the trend is not expected to continue, the project is forecast to be $25,000 under budget.
VAC2 | 33333.3333 | n | If the trend is expected to continue, the project is forecast to be $33,333 under budget.
VAC3 | 48888.8889 | n | If the cost and schedule trends are expected to continue, the project is forecast to be $48,889 under budget.
ETC1 | 125000 | n | If the trend is not expected to continue, $125,000 will be required to complete the project.
ETC2 | 116666.6667 | n | If the trend is expected to continue, $116,667 will be required to complete the project.
ETC3 | 101111.1111 | n | If the cost and schedule trends are expected to continue, $101,111 will be required to complete the project.
TCPI | 0.83333 |  | To complete the project within the original budget, $0.83 worth of value must be received for every dollar spent for the remainder of the project.
Milestones | Due Date | Finish Variance | #days
Mod 2 development complete | 2013-05-30 | -5 days | -5 | Mod 2 development complete is 5 days ahead of schedule.
Mod 3 development complete | 2013-06-15 | 5 days | 5 | Mod 3 development complete is 5 days behind schedule.
Module testing complete | 2013-06-25 | 7 days | 7 | Module testing complete is 7 days behind schedule.