## Issues Log
Issues Log |  |  |  | Project Manager: |  | Rebecca Brown
Project Name: |  | Emanon College Lab Build |  | Revision Date: |  | 2019-03-31
Not Started
In Progress
Closed
Item # | Date | Description of Issue/Risk/Change | Actions Required | Person Responsible | Status | Target Completion Date | Result/Comments | Date of Closure
1 | 2009-03-13 | Plan project took 10d longer, 24h less work, and cost $720 less than planned, due to the Facilities Manager | The schedule slippage is within the total slack, so no action will be taken at this time. | R. Brown | Closed | NA | The start of design activities were delayed by 10d. | 2009-03-13
2 | 2009-03-27 | The project plan approved milestone finished 19d later than expected. | Execution could start based on preliminary approval, so no action is required. | R. Brown | Closed | NA | The project is currently 10d behind schedule | 2009-03-27
3 | 2009-04-03 | Analyse lab requirements took 5d longer, 8h less work, and cost $240 less than planned, due to the Facilities Manager. | Monitor the Facilities Manager's availability and effort. | R. Brown | In Progress
4 | 2009-04-03 | The lab requirements complete milestone finished 15d later than planned. | Investigate opportunities for schedule recovery. | R. Brown | In Progress | 2009-04-30 | The project is currently 15d behind schedule
5 | 2009-05-04 | Develop furniture specs took 5d longer, 4h less work, and cost $120 less than planned, due to the Facilities Manager. | Facilities Manager's availability is limited, and has conflicting priorities. Facilities Manager requested to prioritize project work. | R. Brown | In Progress | 2009-05-31 | The project has slipped to 20d behind schedule.
6 | 2009-05-04 | The Furniture and equipment specs complete milestone finished 20d later than planned. | Remaining tasks will be monitored for completion before construction is scheduled to start. | R. Brown | In Progress | 2009-06-30 | The project is currently 20d behind schedule.
7 | 2009-05-15 | Develop architectural specs took 19d longer than planned. Investigation identified that the Facilities Manager was not available for consultation. | Discuss Facilities Manager's availability with the Facilities Director. | R. Brown | In Progress | 2009-05-31 | The project is currently tracking 33d (7 weeks) behind schedule.
8 | 2009-05-29 | Develop structural specs took 19d longer than planned due to the Facilities Manager. | Facilities Director to reprioritize Facilities Manager's work. | D. Woodrum | In Progress | 2009-06-12 | The project remains 33d behind schedule.
9 | 2009-05-29 | Develop electrical specs took 13d longer than planned due to the Facilities Manager. | Facilities Director to reprioritize Facilities Manager's work. | D. Woodrum | In Progress | 2009-06-12 | The project remains 33d behind schedule.
10 | 2009-06-05 | Develop mechanical specs took 18d longer than planned due to the Facilties Manager. | Facilities Director to direct Facilities Manager's work. | D. Woodrum | In Progress | 2009-06-12 | The project remains 33d behind schedule.
11 | 2009-06-05 | Develop communications/data specs took 18d longer than planned due to the Facilities Manager. | Facilities Director to direct Facilities Manager's work. | D. Woodrum | In Progress | 2009-06-12 | The project remains 33d behind schedule.
12 | 2009-06-12 | Design lab interiors - Borlaug took 8d longer, 32h more work, and $3200 more cost than planned, due to the Interior Designer. | Monitor the Interior Designer's availability and effort. | R. Brown | In Progress | 2009-06-19 | Interior design costs have increased by $3200.
13 | 2009-06-19 | Design lab interiors - Marquez took 13d longer, 32h more work, and $3200 more cost than planned, due to the Interior Designer. | Investigate underestimate of work and duration with Interior Designer | R. Brown | In Progress | 2009-06-26 | Interior design costs have increased by $6400.
14 | 2009-06-26 | Design lab interiors - Salam took 18d longer, 40h more work, and $4000 more cost than planned, due to the Interior Designer. | Finalize contract with Interior Designer and remove from approved vendor list. | R. Brown | In Progress | 2009-06-26 | Interior design costs have increased by $10400.
15 | 2009-06-26 | Design lab interiors - Sen took 18d longer, 40h more work, and $4000 more cost than planned, due to the Interior Designer. | Finalize contract with Interior Designer and remove from approved vendor list. | R. Brown | In Progress | 2009-06-26 | Interior design costs have increased by $14400.
16 | 2009-06-26 | Interior Designer took a total of 144h more work, and cost $14400 more than planned due to underestimating and not being able to devote necessary time to the project. | Finalize contract with Interior Designer and remove from approved vendor list. | R. Brown | Closed | 2009-06-26 | Interior designer has been removed from the project. | 2009-06-26
17 | 2009-06-26 | The designs complete milestone finished 38d later than planned, but within available total slack. | No action is required at this time. | R. Brown | Closed | NA | The project is currently on track to start construction on 5 July 2009. | 2009-06-26
18 | 2009-06-26 | Produce operations & maintenance manuals has not started as expected.