## Issues Log
Issues Log |  |  |  | Project Manager: |  | Rebecca Brown
Project Name: |  | Emanon College Lab Build |  | Revision Date: |  | 2019-03-31
Not Started
In Progress
Closed
Item # | Date | Description of Issue/Risk/Change | Actions Required | Person Responsible | Status | Target Completion Date | Result/Comments | Date of Closure
1 | 2009-03-13 | Plan project took 10d longer, 24h less work, and cost $720 less than planned, due to the Facilities Manager | The schedule slippage is within the total slack, so no action will be taken at this time. | R. Brown | Closed | NA | The start of design activities were delayed by 10d. | 2009-03-13
2 | 2009-03-27 | The project plan approved milestone finished 19d later than expected. | Execution could start based on preliminary approval, so no action is required. | R. Brown | Closed | NA | The project is currently 10d behind schedule | 2009-03-27
3 | 2009-04-03 | Analyse lab requirements took 5d longer, 8h less work, and cost $240 less than planned, due to the Facilities Manager. | Monitor the Facilities Manager's availability and effort. | R. Brown | In Progress
4 | 2009-04-03 | The lab requirements complete milestone finished 15d later than planned. | Investigate opportunities for schedule recovery. | R. Brown | In Progress | 2009-04-30 | The project is currently 15d behind schedule
5 | 2009-05-04 | Develop furniture specs took 5d longer, 4h less work, and cost $120 less than planned, due to the Facilities Manager. | Facilities Manager's availability is limited, and has conflicting priorities. Facilities Manager requested to prioritize project work. | R. Brown | In Progress | 2009-05-31 | The project has slipped to 20d behind schedule.
6 | 2009-05-04 | The Furniture and equipment specs complete milestone finished 20d later than planned. | Remaining tasks will be monitored for completion before construction is scheduled to start. | R. Brown | In Progress | 2009-06-30 | The project is currently 20d behind schedule.
7 | 2009-05-15 | Develop architectural specs took 19d longer than planned. Investigation identified that the Facilities Manager was not available for consultation. | Discuss Facilities Manager's availability with the Facilities Director. | R. Brown | In Progress | 2009-05-31 | The project is currently tracking 33d (7 weeks) behind schedule.
8 | 2009-05-29 | Develop structural specs took 19d longer than planned due to the Facilities Manager. | Facilities Director to reprioritize Facilities Manager's work. | D. Woodrum | In Progress | 2009-06-12 | The project remains 33d behind schedule.
9 | 2009-05-29 | Develop electrical specs took 13d longer than planned due to the Facilities Manager. | Facilities Director to reprioritize Facilities Manager's work. | D. Woodrum | In Progress | 2009-06-12 | The project remains 33d behind schedule.
10 | 2009-06-05 | Develop mechanical specs took 18d longer than planned due to the Facilties Manager. | Facilities Director to direct Facilities Manager's work. | D. Woodrum | In Progress | 2009-06-12 | The project remains 33d behind schedule.
11 | 2009-06-05 | Develop communications/data specs took 18d longer than planned due to the Facilities Manager. | Facilities Director to direct Facilities Manager's work. | D. Woodrum | In Progress | 2009-06-12 | The project remains 33d behind schedule.
12 | 2009-06-12 | Design lab interiors - Borlaug took 8d longer, 32h more work, and $3200 more cost than planned, due to the Interior Designer. | Monitor the Interior Designer's availability and effort. | R. Brown | In Progress | 2009-06-19 | Interior design costs have increased by $3200.
13 | 2009-06-19 | Design lab interiors - Marquez took 13d longer, 32h more work, and $3200 more cost than planned, due to the Interior Designer. | Investigate underestimate of work and duration with Interior Designer | R. Brown | In Progress | 2009-06-26 | Interior design costs have increased by $6400.
14 | 2009-06-26 | Design lab interiors - Salam took 18d longer, 40h more work, and $4000 more cost than planned, due to the Interior Designer. | Finalize contract with Interior Designer and remove from approved vendor list. | R. Brown | In Progress | 2009-06-26 | Interior design costs have increased by $10400.
15 | 2009-06-26 | Design lab interiors - Sen took 18d longer, 40h more work, and $4000 more cost than planned, due to the Interior Designer. | Finalize contract with Interior Designer and remove from approved vendor list. | R. Brown | In Progress | 2009-06-26 | Interior design costs have increased by $14400.
16 | 2009-06-26 | Interior Designer took a total of 144h more work, and cost $14400 more than planned due to underestimating and not being able to devote necessary time to the project. | Finalize contract with Interior Designer and remove from approved vendor list. | R. Brown | Closed | 2009-06-26 | Interior designer has been removed from the project. | 2009-06-26
17 | 2009-06-26 | The designs complete milestone finished 38d later than planned, but within available total slack. | No action is required at this time. | R. Brown | Closed | NA | The project is currently on track to start construction on 5 July 2009. | 2009-06-26
18 | 2009-06-26 | Produce operations & maintenance manuals has not started as expected. | Reschedule all unfinished work to after the status date. | R. Brown | In Progress | 2009-06-26 | The project is now expected to complete 4 weeks behind schedule.
|  |  | Adjust the duration of Monitor and control project to 110d. | R. Brown | In Progress | 2009-06-26 | The project is expected to complete by 31 Aug 2009 and cost of M&C project has reduced by $1134.
19 | 2009-06-26 | The Facilities Manager has taken extended sick leave due to stress. | Replace the Facilities Manager with the Facilities Director on the following tasks: | D. Woodrum | In Progress | 2009-07-05 | The cost of facilities work is $523 less than originally planned.
Monitor & control project
Close project
Produce operations and maintenance manuals
20 | 2009-06-26 | The sponsor has requested that the project be completed before 15 Aug 2009 to accommodate a new lab course starting on 17 Aug 2009. | Set the deadline on Project Complete to 15 Aug 2009. | R. Brown | In Progress | 2009-06-26 | The project is now scheduled to complete 10d after the deadline.
|  |  | Resequence Produce as-built documents with FF dependencies to all "Build lab tasks". | R. Brown | In Progress | 2009-07-31 | This task is now scheduled to complete on July 31.
|  |  | Increase the units of the IS Director and Facilities Director to 50% on Produce operations and maintenance manuals to reduce the duration to 19 days. | R. Brown | In Progress | 2009-07-24 | The task is now scheduled to complete on July 24.
|  |  | Adjust the duration of Monitor & control project to 100d. | R. Brown | In Progress | 2009-08-06 | The cost of M&C project has reduced by $1885.
The project is now scheduled to complete on 13 Aug 2009, ahead of the new deadline.
Note on C11: AMC: As the project progresses variances and issues should be documented to be able to identify trends later.
Note on C13: AMC: Copy the task names directly from the .mpp file. Using the task numbers may be confusing if tasks are added or moved within the .mpp file and the numbers change.
Note on C17: AMC: Variances should always be investigated to determine the source.
Note on D28: AMC: Be very specific about the action being taken. Notice that several actions can be taken to address a single issue.
Note on H29: AMC: Document the impacts of the actions and the final results as comments.