## Threats
Risk Register |  |  |  | Project Manager:
| Project Name: |  |  | Revision Date:
|  | Risk Identification |  |  |  |  | Qualitative Analysis |  |  | Quantitative Analysis |  |  | Response Development |  |  | Monitoring & Control
Priority | ID # | Category | Type | Risk Triggers | Risk Event (Threat or Negative Risks) | Risk Symptoms | Probability Low - High 1-2-3-4-5 | Impact Low - High 1-2-3-4-5 | Score Prob x Imp | Probability % | Quantified Impact | Exposure Prob x Imp | Response Type | Response Strategy | Owner Responsible | Monitoring Action | Monitoring Timing | Status
|  |  | Objective | [9 empty] | Avoid
|  |  | Deliverable | [9 empty] | Transfer
|  |  | Work | [9 empty] | Mitigate
|  |  | Resource | [9 empty] | Accept (Active)
|  |  | Schedule | [9 empty] | Accept (Passive)
|  |  | Budget | [9 empty] | Escalate
Stakeholder
Communication
External
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Note on K3: AMC : Should only be conducted on risks as required by risk tolerances.
Note on A4: AMC : Priority number assigned by the project development team to the risk.
Note on B4: AMC : Unique identifier for this risk assigned by the team for tracking purposes. Valid entries are alpha, numeric or combination of both.
Note on C4: AMC : Broadly-defined area of risk for organization. Usually categories are created as part of risk identification and organization of the risk list.
Note on D4: AMC : Major impact area for the risk.
Note on E4: AMC : Detailed description of the situation, condition, event or circumstance that could precipitate the risk.
Note on F4: AMC : Specific definition of the risk event that could occur on the project.
Note on G4: AMC : Indicator that the risk has occured. Used to determine when to implement the risk response strategy.
Note on H4: AMC : Qualitative assessment of the likelihood of the risk occurring.
Note on I4: AMC : The severity of the risk's effect on the project objectives.
Note on J4: AMC : Automatically calculated. Product of the qualitative probability and impact. Thresholds and required actions are based on the selected risk matrix defined in the risk management plan and included as a worksheet in this document. After qualification, risks should be sorted and prioritized by this score.
Note on K4: AMC : Quantified assessment of the percentage likelihood of the risk occurring.
Note on L4: AMC : Quantified assessment of the impact on the project objectives in measurable terms (e.g. dollars, days, quality, etc.)
Note on M4: AMC : Should be calculated product of quantified probability and impact values.
Note on N4: AMC : The response type that is most likely to be effective for each risk. Valid entries are Avoidance, Transference, Mitigation, Exploit, Share, Enhance, Active acceptance or Passive acceptance.
Note on O4: AMC : Detailed response action to be taken to address the risk.
Note on P4: AMC : Name(s) or role(s) of person or people responsible for the risk.
Note on Q4: AMC : Action(s) required to monitor and control the risks and/or implement any contingency plans.
Note on R4: AMC : Frequency or timing of monitoring and controlling actions.
Note on S4: AMC : Status of the risk and/or response, including active, dormant or retired status and detailed explanation.

## Opportunities
Risk Register |  |  |  | Project Manager:
| Project Name: |  |  | Revision Date:
|  | Risk Identification |  |  |  |  | Qualitative Analysis |  |  | Quantitative Analysis |  |  | Response Development |  |  | Monitoring & Control
Priority | ID # | Category | Type | Risk Triggers | Risk Event (Opportunities or Positive Risks) | Risk Symptoms | Probability Low - High 1-2-3-4-5 | Impact Low - High 1-2-3-4-5 | Score Prob x Imp | Probability % | Quantified Impact | Exposure Prob x Imp | Response Type | Response Strategy | Owner Responsible | Monitoring Action | Monitoring Timing | Status
|  |  | Objective | [9 empty] | Exploit
|  |  | Deliverable | [9 empty] | Share
|  |  | Work | [9 empty] | Enhance
|  |  | Resource | [9 empty] | Accept (Active)
|  |  | Schedule | [9 empty] | Accept (Passive)
|  |  | Budget | [9 empty] | Escalate
Stakeholder
Communication
External
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Note on K3: AMC : Should only be conducted on risks as required by risk tolerances.
Note on A4: AMC : Priority number assigned by the project development team to the risk.
Note on B4: AMC : Unique identifier for this risk assigned by the team for tracking purposes. Valid entries are alpha, numeric or combination of both.
Note on C4: AMC : Broadly-defined area of risk for organization. Usually categories are created as part of risk identification and organization of the risk list.
Note on D4: AMC : Major impact area for the risk.
Note on E4: AMC : Detailed description of the situation, condition, event or circumstance that could precipitate the risk.
Note on F4: AMC : Specific definition of the risk event that could occur on the project.
Note on G4: AMC : Indicator that the risk has occured. Used to determine when to implement the risk response strategy.
Note on H4: AMC : Qualitative assessment of the likelihood of the risk occurring.
Note on I4: AMC : The severity of the risk's effect on the project objectives.
Note on J4: AMC : Automatically calculated. Product of the qualitative probability and impact. Thresholds and required actions are based on the selected risk matrix defined in the risk management plan and included as a worksheet in this document. After qualification, risks should be sorted and prioritized by this score.
Note on K4: AMC : Quantified assessment of the percentage likelihood of the risk occurring.
Note on L4: AMC : Quantified assessment of the impact on the project objectives in measurable terms (e.g. dollars, days, quality, etc.)
Note on M4: AMC : Should be calculated product of quantified probability and impact values.
Note on N4: AMC : The response type that is most likely to be effective for each risk. Valid entries are Avoidance, Transference, Mitigation, Exploit, Share, Enhance, Active acceptance or Passive acceptance.
Note on O4: AMC : Detailed response action to be taken to address the risk.
Note on P4: AMC : Name(s) or role(s) of person or people responsible for the risk.
Note on Q4: AMC : Action(s) required to monitor and control the risks and/or implement any contingency plans.
Note on R4: AMC : Frequency or timing of monitoring and controlling actions.
Note on S4: AMC : Status of the risk and/or response, including active, dormant or retired status and detailed explanation.

## Sample
Risk Register |  |  |  | Project Manager: | Rebecca Brown
| Project Name: | Lab Build Project |  | Revision Date: | March 1, 20XX
|  | Risk Identification |  |  |  |  | Qualitative Analysis |  |  | Quantitative Analysis |  |  | Response Development |  |  | Monitoring & Control
Priority | ID # | Category | Type | Risk Triggers | Risk Event (Threat or Opportunity) | Risk Symptoms | Probability | Impact | Score | Probability % | Quantified Impact | Exposure | Response Type | Response Strategy | Owner Responsible | Monitoring Action | Monitoring Timing | Status
|  |  | Objective | [9 empty] | Avoid
|  |  | Deliverable | [9 empty] | Transfer
|  |  | Work | [9 empty] | Mitigate
|  |  | Resource | [9 empty] | Exploit
|  |  | Schedule | [9 empty] | Share
|  |  | Budget | [9 empty] | Enhance
|  |  | Stakeholder | [9 empty] | Accept (Active)
|  |  | Communication | [9 empty] | Accept (Passive)
External
| 1 | Technical | Work | Facilities group are not notified of building schedule with sufficient time to remove equipment. | Rooms are not emptied of existing lab equipment or furniture before new lab construction is scheduled to begin. | Construction contractor notification of equipment in room. | 2 | 3 | 6 | NA | NA | NA | Mitigate | Notify all facilities staff of construction schedule for existing rooms as soon as known, two weeks before construction begins, and one week before construction begins. | Facilities Manager | Review of the status of schedule dependencies on room construction activities at monthly meetings (Agenda item) | Monthly Two-weeks before demolition starts One week before demolition starts
| 2 | [7 empty] | 0
| 3 | [7 empty] | 0
| 4 | [7 empty] | 0
| 5 | [7 empty] | 0
| 6 | [7 empty] | 0
| 7 | [7 empty] | 0
| 8 | [7 empty] | 0
| 9 | [7 empty] | 0
| 10 | [7 empty] | 0
| 11 | [7 empty] | 0
| 12 | [7 empty] | 0
| 13 | [7 empty] | 0
| 14 | [7 empty] | 0
| 15 | [7 empty] | 0
| 16 | [7 empty] | 0
| 17 | [7 empty] | 0
| 18 | [7 empty] | 0
| 19 | [7 empty] | 0
| 20 | [7 empty] | 0
| 21 | [7 empty] | 0
| 22 | [7 empty] | 0

## Risk Matrix
Risk Matrix (Linear)
Probability | 5 | 25 | 20 | 15 | 10 | 5 | 5 | 10 | 15 | 20 | 25 | >14 | High Risk - Requires quantification and response development
| 4 | 20 | 16 | 12 | 8 | 4 | 4 | 8 | 12 | 16 | 20 | 5-14 | Moderate Risk - Requires response development, but not quantification
| 3 | 15 | 12 | 9 | 6 | 3 | 3 | 6 | 9 | 12 | 15 | <5 | Low Risk - Requires active or passive acceptance
| 2 | 10 | 8 | 6 | 4 | 2 | 2 | 4 | 6 | 8 | 10
| 1 | 5 | 4 | 3 | 2 | 1 | 1 | 2 | 3 | 4 | 5
|  | 5 | 4 | 3 | 2 | 1 | 1 | 2 | 3 | 4 | 5
|  | Opportunity Impact |  |  |  |  | Threat Impact
Risk Matrix (Non-linear)
Probability | 5 | 80 | 40 | 20 | 10 | 5 | 5 | 10 | 20 | 40 | 80 | >16 | High Risk - Requires quantification and response development
| 4 | 64 | 32 | 16 | 8 | 4 | 4 | 8 | 16 | 32 | 64 | 8-16 | Moderate Risk - Requires response development, but not quantification
| 3 | 48 | 24 | 12 | 6 | 3 | 3 | 6 | 12 | 24 | 48 | <8 | Low Risk - Requires active or passive acceptance
| 2 | 32 | 16 | 8 | 4 | 2 | 2 | 4 | 8 | 16 | 32
| 1 | 16 | 8 | 4 | 2 | 1 | 1 | 2 | 4 | 8 | 16
|  | 16 | 8 | 4 | 2 | 1 | 1 | 2 | 4 | 8 | 16
|  | Impact |  |  |  |  | Impact