## MM-DD-YYYY
Weekly Operations Status Report
Department | Report Date
Group
Manager
Overall Status/Key Performance Indicators |  | Status
Business Processes
Resources/Staffing
Financial
Customer Satisfaction
Projects
Activities/Accomplishments
Concerns/Potential Issues |  | Exposure
Actions/Steps to Address Concerns/Potential Issues |  | Priority
Major Decisions Made
Planned Activities for Next Period

## Sample
Weekly Operations Status Report
Department | Operations | Report Date | 2004-05-13
Group | Customer Service
Manager | Wanda Irganizit
Overall Status/Key Performance Indicators |  |  | Status |  | Note that any of the colour-coded cells can be changed to symbol dropdowns instead of simple colours. See the "Dropdown" worksheet for samples of the symbols dropdown.
Business Processes |  |  | Hindered
Resources/Staffing |  |  | Blocked
Financial |  |  | Hindered
Customer Satisfaction |  |  | Controlled
Projects/Programs |  |  | Hindered
Activities/Accomplishments
- Completed 75% of outstanding MAC requests (15 remaining)
- Achieved Milestone 21 on Project XYZ
- Completed closeout of Project ABC
- Repaired network failure due to worm
Concerns/Potential Issues |  |  | Exposure
- Potential labour dispute scheduled for next week |  |  | Caution
- Overallocation of staff in upcoming weeks |  |  | Critical
- Project XYZ cost variance is approaching unacceptable levels |  |  | Caution
Actions/Steps to Address Concerns/Potential Issues |  |  | Priority
- Planning to complete critical activities to sustainment before scheduled work action |  |  | Vital
- Renegotiating schedules and scope of concurrent projects to level staff utilization |  |  | Vital
- Investigating potential future cost savings on Project XYZ to recover variance as soon as possible |  |  | Normal
Major Decisions Made |  |  |  |  | Note: This section can be adjusted to include a description of projects being completed, any upcoming projects and potential stakeholders, etc.
- Approved Charter for new FGH project to commence in three weeks
- Terminated Project KLM due to shift in strategic direction of organization
- Seconded D. Ducke to Integration Dept. for 6 month assignment
Planned Activities for Next Period
- Initiation of Phase 4 on Project UVW
- Develop departmental Mission statement with all group managers
- Start quarterly staff reviews
- Complete remainder of outstanding MAC requests
Note: This table can have data for planned and actual

## Cash Flow Report
Cash Flow | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC
Opening Cash Balance (1000's) | 8000 | 7507.3 | 7089.6 | 6501.1 | 6007.6 | 5459.1 | 5020.6 | 4382.1 | 3871.6 | 3183.1 | 2449.6 | 1281.1
COSTS
LABOUR
Direct Labour (Salary) | 95.5 | 95.5 | 95.5 | 95.5 | 95.5 | 95.5 | 95.5 | 95.5 | 95.5 | 95.5 | 95.5 | 95.5
Sub-contractors | 4.2 | 4.2 | 100 | 80 | 60 | 25 | 150 | 97 | 200 | 320 | 680 | 120
TOTAL LABOUR | 99.7 | 99.7 | 195.5 | 175.5 | 155.5 | 120.5 | 245.5 | 192.5 | 295.5 | 415.5 | 775.5 | 215.5
SUPPLIES
Office Supplies | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
Periodicals & Books
Shipping & Postage
Other Supplies
Lab Supplies
TOTAL SUPPLIES | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
EQUIPMENT & FACILITIES
Facility Rent
Facility Parking
Building Supplies
Building Services
Equipment Rent | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
Equipment Maintenance
Amort - Leasehold Improvements
Deprec - Furn & Equip
Deprec - Elec Equip.
Deprec - PCs | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
Deprec - Computers
Deprec - Vehicles
Utilities
Amort. Non-Compete
Telephone & Fax | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180
Capital Lease Obligation
Computer Costs
Website Hosting | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
Amortization/Trademark
Copying Costs | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
Telephone/Data | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60
Fixed Asset Leasing
Uncapitalized Furn & Equip
Direct Cost Offset
Disposition of Assets
TOTAL EQUIPMENT & FACILITIES | 293 | 293 | 293 | 293 | 293 | 293 | 293 | 293 | 293 | 293 | 293 | 293
TRAVEL & RELOCATION
Business Conferences
Employment Expense
Indirect Travel
Employee Relocation
Misc. Employee Expenses
Employment Agency Fees
Employee Education
Hours Worked Diff.
Cert Course Instr Exp
Cert Course Student Exp
Cert Course Payback Exp
Car Leasing & Rental
Company Car Expenses
Car Allowance
TOTAL TRAVEL & RELOCATION | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SERVICES
Insurance
Accounting
Bookeeping
Taxes & Licenses
Consultants
Miscellaneous Services
Temporary Services
Legal
Graphics Costs
Training Expenses
Business Development
Commissions
Printing
Operations Variable Pay | JAN: 75; MAR: 75; MAY: 75; JUL: 75; SEP: 75; NOV: 75; DEC: 125
Corporate Memberships
Employee Referal
Bank Charges | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
Restructuring
TOTAL SERVICES | 95 | 20 | 95 | 20 | 95 | 20 | 95 | 20 | 95 | 20 | 95 | 145
OTHER EXPENSES
Contributions
Interest Expense
Goodwill Amortization
Bad Debt Expense
Acquisition Costs
Travel
Entertainment
Relocation
Penalties/Fees
Emp Relocation Exp
Protest Costs
TOTAL OTHER EXPENSES | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL CASH OUT | 492.7 | 417.7 | 588.5 | 493.5 | 548.5 | 438.5 | 638.5 | 510.5 | 688.5 | 733.5 | 1168.5 | 658.5
CLOSING CASH BALANCE | 7507.3 | 7089.6 | 6501.1 | 6007.6 | 5459.1 | 5020.6 | 4382.1 | 3871.6 | 3183.1 | 2449.6 | 1281.1 | 622.6

## Blank
Weekly Operations Status Report
Department | Report Date
Group
Manager
Overall Status/Key Performance Indicators |  | Status
Business Processes
Resources/Staffing
Financial
Customer Satisfaction
Projects
Activities/Accomplishments
Concerns/Potential Issues |  | Exposure
Actions/Steps to Address Concerns/Potential Issues |  | Priority
Major Decisions Made
Planned Activities for Next Period

## Dropdowns
Exposure | Status | Priority | Departments | Group | Symbol
Critical | Controlled | Vital | Operations | Customer Service | ¢
Caution | Hindered | Urgent | Human Resources | Information Technology | ¿
Moderate | Blocked | Normal | Special Projects | Labour Relations | Ä
|  |  | Administration | Training
|  |  | Marketing | Promotions
Sales
Sample Row