## Task Expense Statement
Task Expense Summary
Summary Tasks | Costs
Project Management | 38080
Design | 101120
Construction
Borlaug Building | 271400
Marquez Library | 271400
Salam Center | 407100
Sen Building | 407100
Commissioning | 17600
Sub-total | 1513800
Contingency | 151200
Total | 1665000

## Resource Expense Statement
Resource Expense Summary
Resource Group | Costs
Administration | 29600
Design | 127200
Equipment | 958000
Furniture | 199000
General Contractor | 200000
Sub-total | 1513800
Contingency | 151200
Total | 1665000

## Cash Flow Summary
Cash Flow Summary
Monthly
Tasks | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug
Project Management | 4100 | 17700 | 2097.45 | 2002.12 | 1906.78 | 2065.45 | 1985.45 | 6222.74
Design | Mar: 40016; Apr: 59664; May: 1440
Construction | Jul: 1353000; Aug: 4000
Commissioning |  |  |  | 1120 | 1680 | 0 | 0 | 14800
Sub-total | 4100 | 17700 | 42113.45 | 62786.12 | 5026.78 | 2065.45 | 1354985.45 | 25022.74
Cumulative total | 4100 | 21800 | 63913.45 | 126699.57 | 131726.35 | 133791.8 | 1488777.25 | 1513799.99
Total with contingency | 1665000 | 1665000 | 1665000 | 1665000 | 1665000 | 1665000 | 1665000 | 1665000
Weekly
Tasks | 2009-01-04 | 2009-01-11 | 2009-01-18 | 2009-01-25 | 2009-02-01 | 2009-02-08 | 2009-02-15 | 2009-02-22 | 2009-03-01 | 2009-03-08 | 2009-03-15 | 2009-03-22 | 2009-03-29 | 2009-04-05 | 2009-04-12 | 2009-04-19 | 2009-04-26 | 2009-05-03 | 2009-05-10 | 2009-05-17 | 2009-05-24 | 2009-05-31 | 2009-06-07 | 2009-06-14 | 2009-06-21 | 2009-06-28 | 2009-07-05 | 2009-07-12 | 2009-07-19 | 2009-07-26 | 2009-08-02 | 2009-08-09 | 2009-08-16 | 2009-08-23
Project Management | 1025 | 1025 | 1025 | 1025 | 1025 | 1025 | 14625 | 1025 | 476.69 | 476.69 | 476.69 | 476.69 | 476.69 | 381.36 | 476.69 | 476.69 | 476.69 | 476.69 | 476.69 | 381.36 | 476.69 | 476.69 | 476.69 | 476.69 | 476.69 | 317.36 | 396.69 | 476.69 | 476.69 | 476.69 | 349.36 | 396.69 | 396.69 | 5080
Design | 2009-03-01: 7600; 2009-03-08: 7600; 2009-03-15: 13840; 2009-03-22: 7840; 2009-03-29: 7840; 2009-04-05: 22080; 2009-04-12: 22800; 2009-04-19: 7200; 2009-04-26: 3600; 2009-05-03: 720
Construction | 2009-07-05: 557966.67; 2009-07-12: 520442.86; 2009-07-19: 48190.48; 2009-07-26: 226400; 2009-08-02: 4000
Commissioning | 2009-04-19: 560; 2009-04-26: 700; 2009-05-03: 700; 2009-05-10: 700; 2009-05-17: 140; 2009-05-24: 0; 2009-05-31: 0; 2009-06-07: 0; 2009-06-14: 0; 2009-06-21: 0; 2009-06-28: 0; 2009-07-05: 0; 2009-07-12: 0; 2009-07-19: 0; 2009-07-26: 0; 2009-08-02: 4338.46; 2009-08-09: 5230.77; 2009-08-16: 5230.77
Sub-total | 1025 | 1025 | 1025 | 1025 | 1025 | 1025 | 14625 | 1025 | 8076.69 | 8076.69 | 14316.69 | 8316.69 | 8316.69 | 22461.36 | 23276.69 | 8236.69 | 4776.69 | 1896.69 | 1176.69 | 521.36 | 476.69 | 476.69 | 476.69 | 476.69 | 476.69 | 317.36 | 558363.36 | 520919.55 | 48667.17 | 226876.69 | 8687.82 | 5627.46 | 5627.46 | 5080
Cumulative total | 1025 | 2050 | 3075 | 4100 | 5125 | 6150 | 20775 | 21800 | 29876.69 | 37953.38 | 52270.07 | 60586.76 | 68903.45 | 91364.81 | 114641.5 | 122878.19 | 127654.88 | 129551.57 | 130728.26 | 131249.62 | 131726.31 | 132203 | 132679.69 | 133156.38 | 133633.07 | 133950.43 | 692313.79 | 1213233.34 | 1261900.51 | 1488777.2 | 1497465.02 | 1503092.48 | 1508719.94 | 1513799.94
Total with contingency | 1665000 | 1665000 | 1665000 | 1665000 | 1665000 | 1665000 | 1665000 | 1665000 | 1665000 | 1665000 | 1665000 | 1665000 | 1665000 | 1665000 | 1665000 | 1665000 | 1665000 | 1665000 | 1665000 | 1665000 | 1665000 | 1665000 | 1665000 | 1665000 | 1665000 | 1665000 | 1665000 | 1665000 | 1665000 | 1665000 | 1665000 | 1665000 | 1665000 | 1665000
Earned Value | 820 | 1640 | 2460 | 3280 | 4100 | 4920 | 5740 | 20160 | 20980 | 21800 | 27343.36 | 32886.72 | 38430.08 | 49600.77 | 58764.13 | 66727.49 | 88749.52 | 110078.21 | 115954.91 | 117776.26 | 120052.96 | 122885.52 | 126088.7 | 128291.87 | 129778.64
Actual Cost | 947 | 1894 | 2841 | 3788 | 4735 | 5682 | 20229 | 21176 | 21248 | 21320 | 29236.69 | 37153.39 | 37710.08 | 45751.94 | 50980.27 | 56666.88 | 67956.26 | 83659.19 | 100042.11 | 110933.28 | 124207.24 | 133681.45 | 139533.38 | 143323.56 | 145882.98
A cumulative cost curve chart shows the expenses over time. This was made from the weekly timescale data, but the bottom axis was reformatted to only display the months. This keeps the information consistent, but gives more data points for a more accurate line. Adding the EV and AC lines will require reformatting the legend.
Note on A21: AMC: This data is copied from the Task Usage view of the .mpp file as BCWP. It is plotted in the chart as "Work Performed" for plain language.
Note on A22: AMC: This data is copied from the Task Usage view of the .mpp file as ACWP. The text in these cells have been coloured similarly to the chart.