## Worksheet
Earned Value Calculation Table
BCWS | BCWP | ACWP | BAC | % Work Complete | % Complete | Physical % Complete
PV | 0 |  | The project planned to have completed $0,000 worth of work by the status date.
EV | 0 |  | The project has completed $0,000 worth of work by the status date.
AC | 0 |  | The project has spent $0,000 as of the status date.
BAC | 0 |  | The total budget of the project is $0,000.
% Work Complete | 0% |  | The project has completed 0% of its total work.
% Duration Complete | 0% |  | The project has completed 0% of its total duration.
Physical % Complete | 0% |  | The project has completed 0% of its physical deliverables.
% Value Complete | #DIV/0! |  | #DIV/0!
% Spent | #DIV/0! |  | #DIV/0!
CV | 0 | #DIV/0! | The project is exactly on budget.
SV | 0 | #DIV/0! | The project is exactly on schedule.
CPI | #DIV/0! | #DIV/0! | #DIV/0!
SPI | #DIV/0! | #DIV/0! | #DIV/0!
EAC1 | 0 | #DIV/0! | If the trend is not expected to continue, the project is forecast to cost $0,000.
EAC2 | #DIV/0! | #DIV/0! | #DIV/0!
EAC3 | #DIV/0! | #DIV/0! | #DIV/0!
VAC1 | 0 | #DIV/0! | If the trend is not expected to continue, the project is forecast to be exactly on budget.
VAC2 | #DIV/0! | #DIV/0! | #DIV/0!
VAC3 | #DIV/0! | #DIV/0! | #DIV/0!
ETC1 | 0 | #DIV/0! | If the trend is not expected to continue, $0,000 will be required to complete the project.
ETC2 | #DIV/0! | #DIV/0! | #DIV/0!
ETC3 | #DIV/0! | #DIV/0! | #DIV/0!
TCPI | #DIV/0! |  | #DIV/0!
Milestones | Due Date | Finish Variance | #days
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
Note on B29: AMC: Paste Baseline Finish dates in this column
Note on C29: AMC: Paste Finish Variance column for milestones here.

## Sample
Earned Value Calculation Table
BCWS | BCWP | ACWP | BAC | % Work Complete | % Complete | Physical % Complete
325000 | 375000 | 350000 | 500000 | 60% | 83.33% | 80%
PV | 325000 |  | The project planned to have completed $325,000 worth of work by the status date.
EV | 375000 |  | The project has completed $375,000 worth of work by the status date.
AC | 350000 |  | The project has spent $350,000 as of the status date.
BAC | 500000 |  | The total budget of the project is $500,000.
% Work Complete | 60% |  | The project has completed 60% of its total work.
% Duration Complete | 83.33% |  | The project has completed 83% of its total duration.
Physical % Complete | 80% |  | The project has completed 80% of its physical deliverables.
% Complete | 75% |  | The project has completed 75% of its value.
% Spent | 70% |  | The project has spent 70% of the budget.
CV | 25000 | n | The project is $25,000 under budget.
SV | 50000 | n | The project is $50,000 ahead of schedule.
CPI | 1.0714 | n | The project is receiving $1.07 worth of value for every dollar spent.
SPI | 1.1538 | n | The project is progressing 15% faster than planned.
EAC1 | 475000 | n | If the trend is not expected to continue, the project is forecast to cost $475,000.
EAC2 | 466666.6667 | n | If the trend continues, the project is forecast to cost $466,667.
EAC3 | 451111.1111 | n | If the cost and schedule trends continue, the project is forecast to cost $451,111.
VAC1 | 25000 | n | If the trend is not expected to continue, the project is forecast to be $25,000 under budget.
VAC2 | 33333.3333 | n | If the trend is expected to continue, the project is forecast to be $33,333 under budget.
VAC3 | 48888.8889 | n | If the cost and schedule trends are expected to continue, the project is forecast to be $48,889 under budget.
ETC1 | 125000 | n | If the trend is not expected to continue, $125,000 will be required to complete the project.
ETC2 | 116666.6667 | n | If the trend is expected to continue, $116,667 will be required to complete the project.
ETC3 | 101111.1111 | n | If the cost and schedule trends are expected to continue, $101,111 will be required to complete the project.
TCPI | 0.83333 |  | To complete the project within the original budget, $0.83 worth of value must be received for every dollar spent for the remainder of the project.
Milestones | Due Date | Finish Variance | #days
Project approved | 2013-01-01 | 0 days | 0 | Project approved is exactly on schedule.
Module designs complete | 2013-02-15 | -2 days | -2 | Module designs complete is 2 days ahead of schedule.
Mod 1 development complete | 2013-04-15 | -1 days | -1 | Mod 1 development complete is 1 days ahead of schedule.
Mod 2 development complete | 2013-05-30 | -5 days | -5 | Mod 2 development complete is 5 days ahead of schedule.
Mod 3 development complete | 2013-06-15 | 5 days | 5 | Mod 3 development complete is 5 days behind schedule.
Module testing complete | 2013-06-25 | 7 days | 7 | Module testing complete is 7 days behind schedule.
Project complete | 2013-06-30 | 10 days | 10 | Project complete is 10 days behind schedule.