## Issues Log
Issues Log |  |  |  | Project Manager: |  | Rebecca Brown
Project Name: |  | Emanon College Lab Build |  | Revision Date: |  | 2009-06-26
Not Started
In Progress
Closed
Item # | Date | Description of Issue/Risk/Variance/Change | Actions Required | Person Responsible | Status | Target Completion Date | Result/Comments | Date of Closure
1 | 2009-03-13 | Project planning completed 2 weeks later than originally planned due to delays with facilities input. Because this is not a critical activity, it has only delayed the Design phase by two weeks, but not the project. | The schedule slippage is within the total float on the Design tasks, so no action is required unless further delays occur on subsequent tasks. | R. Brown | Closed | NA | The start of design activities were delayed, but further slippages occurred. | 2009-03-13
2 | 2009-03-27 | Project plan approval was received 2 weeks after planning work was completed | Work to continue as scheduled in anticipation of approval because delay is not related to challenges with the plan. | R. Brown | Closed | NA | Project continued as planned and plan approval was received on March 27, 2009. | 2009-03-27
3 | 2009-04-03 | Analyse Lab Requirements took 5 days longer than planned. | Variance is within total slack and not expected to become a trend at this point. | R. Brown | Closed | NA |  | 2009-04-03
|  | Facilities Manager performed 8h less work than planned and took 5d longer than planned. | Performance of Facilities Manager to be monitored.
4 | 2009-05-04 | Developing furniture specs took 1 week longer than planned. Investigation into issue identified challenges with conflicting time commitments for Interior Designer | Review task priority with Interior Designer The schedule slippage is within the total float, so no action is required unless further delays occur. | R. Brown | Closed | NA |  | 2009-05-04
5 | 2009-06-05 | Construction documents complete 7 weeks behind schedule. | Facilities Director has been notified of Facilities manager's performance and disciplinary actions will be initiated. | D. Woodrum | In Progress | 2009-06-12
Develop architectural specs took 19d longer than planned
Develop structural specs took 18d longer than planned
Develop electrical specs took 13d longer than planned
Develop mechanical specs took 18d longer than planned
Develop communications/data specs took 18d longer than planned
Investigation identified that Facilities Manager has consistently caused delays on design tasks by not providing required documents in a timely manner.
6 | 2009-06-12 | Design lab interiors - Borlaug took 8d longer than planned and required 32h more work and $4,400 more cost than planned. | Facilities manager is required to send all documentation for all buildings and rooms to Interior Designer as soon as possible. | D. Woodrum | In Progress | 2009-06-12
Interior Designer has expressed that there are communication problems with the Facilities Manager while trying to complete documentation.
7 | 2009-06-19 | Design lab interiors - Marquez took 13d longer than planned and required 32h more work and $4,000 more cost than planned. |  | R. Brown | Closed | 2009-06-26 | All interior designs were completed by 26 Jun 09 | 2009-06-26
|  | Interior Designer has underestimated design work by 100% on all design tasks. | Double estimates of work on remaining Interior Design tasks. Estimates will be: |  |  |  | $17,200 more cost. This variance will be controlled with contingency.
|  |  | Design lab interiors - Salam = 80h work $8,800 cost |  |  |  | 144h more work
|  |  | Design lab interiors - Sen = 80h work $8,000 cost |  |  |  | 18d more duration
|  | Total slack on remaining Interior Design tasks has been used up. Tasks have become critical and must be completed by 26 Jun 09 | Tasks will be completed no later than 26 Jun 09 |  |  |  | 8 weeks behind schedule
Adjust remaining estimates with this Interior Designer on other projects.
7 | 2009-06-26 | Designs complete 8 weeks behind schedule, but within total float. Facilities manager delayed interior design activities, and has been removed from the project. | Facilities Director will replace Facilities Manager on the following tasks: | R. Brown | In Progress | 2009-07-06 | Cost difference as a result of this resource replacement is negligible.
|  |  | Monitor & control project | D. Woodrum | In Progress |  | Facilities manager has been replaced on the task. Facilities Director has been assigned for the same number of hours to reflect learning curve and more efficient work.
|  |  | Produce operations and maintenance manuals | D. Woodrum | In Progress |  | Facilities manager has been replaced on the task. Facilities Director has been assigned for the same number of hours to reflect learning curve and more efficient work.
|  |  | Close project | D. Woodrum | In Progress |  | Facilities manager has been replaced on the task. Facilities Director has been assigned for the same number of hours to reflect learning curve and more efficient work.
|  | Produce operations and maintenance manuals has not started and is currently 8 weeks behind schedule | Produce operations and maintenance manuals must be rescheduled to be completed after June 26 | R. Brown | In Progress | 2009-08-06 | This task will now be completed on August 6.
8 | 2009-06-26 | Sponsor has requested that project be completed before August 15, 2009. | Change the deadline date on Project Complete to August 15. | R. Brown | In Progress | 2009-08-14 | New deadline set.
|  |  | Assign General Contractor to Produce operations and maintenance manuals for 24h and reduce IS Director and Fac. Manager to 32h each to reduce the duration of the task to 25d. | R. Brown | In Progress | 2009-06-29 | Crashed task by adding resources to reduce duration. This task will now be compeleted by August 4.
|  |  | General Contractor will assign 2.5 people to complete Build Lab S324 to complete in 4d duration. | General Contractor | In Progress | 2009-07-28 | Crashed task by adding resources to reduce duration. This task will now finish on July 31.
|  |  | Reschedule Produce as-built documents for all labs to be completed concurrently with the lab build tasks. | R. Brown | In Progress | 2009-08-04 | Fast-tracked task to complete concurrently with lab build tasks. This task will now finish on August 4 and project will be completed by August 15 according to the requested change.
|  |  | Reduce duration of Monitor & control project to 101 days to account for shortened project duration. | R. Brown | In Progress | 2009-06-28 | Reduced duration to reflect overall project duration reduction. Cost of this task was reduced by $2000.
Note on C11: AMC: As the project progresses variances and issues should be documented to be able to identify trends later.
Note on C17: AMC: Copy the task names directly from the .mpp file. Using the task numbers may be confusing if tasks are added or moved within the .mpp file and the numbers change.
Note on C22: AMC: Variances should always be investigated to determine the source.
Note on D27: AMC: Be very specific about the actions being taken. Notice that several actions can be defined for a single issue.
Note on H26: AMC: Document the impacts of the actions and the final results as comments.