## Lessons Learned
Lessons Learned |  |  |  | Project Manager: | Rebecca Brown
| Project Name: | Lab Build |  | Revision Date: | 2009-08-12
Priority | ID # | Category | Type | Lesson | Background | Benefit | Implementation | Responsible | Status
Objective
Deliverable
Work
Resource
Schedule
Budget
Stakeholder
Communication
External
1 | 1 | Operations | Resource | Project team members must understand the priority of the project in relation to operational and other project work. | One of the project team members was consistently underperforming and completing tasks later than planned. It was identified that this person did not consider the project to be as high priority as his other work, and therefore would not assign the necessary time in his schedule to the project work. | Providing the priority of the project in relation to the other organizational work decreases the probability of schedule slippages or late activities, and it increases the quality of the work and deliverables, because team members devote sufficient effort and time to their assigned activities. | A formal system of project prioritization using a weighted scoring model must be implemented for the entire organization's project portfolio. | Luana Mares Director, Operations | The weighted scoring model will be developed as part of the establishment of a PMO at Emanon College. A prioritization training course has been implemented for all employees, which includes tools and techniques.
Team members will also be provided with a task prioritizer template, and will be given the priority of the project task to be able to incorporate it with the rest of their work priorities.
Note on A4: AMC : Priority value for the lesson.
Note on B4: AMC : Unique identifier for the lesson assigned by the team for tracking purposes. Valid entries are alpha, numeric or combination of both.
Note on C4: AMC : Broadly-defined area of the lesson for organization.
Note on D4: AMC : Area affected by the lesson.
Note on E4: AMC : Specific definition of the lesson as a new skill or competency that has been developed within the organization a a result of the project.
Note on F4: AMC : Detailed description of the situation that created the lesson.
Note on G4: AMC : Description of the benefits that will be realized as a result of the lesson.
Note on H4: AMC : Action plan for improving systems, processes, policies or tools to realize the benefit of the lesson. Lessons learned should result in improvements to the system so that they do not have to be remembered.
Note on I4: AMC : Name(s) or role(s) of person or people responsible for implementing the improvement actions.
Note on J4: AMC : Status of the lesson implementation.