## Scale Evaluation
Project Scale Evaluation
This questionnaire contains criteria to define the scale of each initiative. Next to each statement, click the dropdown arrow to select the response which represents your understanding of the scale of the initiative in each category.
| Criteria | Responses
1 | Scope Range |  | 0
2 | Organization Impact |  | 0
3 | Effort Range |  | 0
4 | Number of Project Team Members |  | 0
5 | Duration Range |  | 0
6 | Complexity |  | 0
7 | Cost Range |  | 0
8 | Stability |  | 0
| Scale: | Not all dropdowns are filled | Not all dropdowns are filled
What are the major risks or issues with the initiative or project?
[Review the list above and identify any risks or issues with the initiative.]
| Process | Detail
Project Initiation/Approval
Deliverable Definition
Task List
Resource Assignments
Schedule
Budget
Risk Planning
Progress Tracking
Reporting
Closing/Termination

## Scales (hidden)
Scales
| Scope/Deliverables | Impact | Effort Estimate | Number of Project Team Members | Duration Estimate | Tasks/Complexity | Cost | Stability | Project Size
| <10 components of 1-2 deliverables | Internal Division/Unit | <=40 hours | 1-2 people | <=5d | 1-20 tasks | <=$10,000 | Requirements are well-understood and reasonably stable | Minor Initiative
| 3-5 deliverables | Multi-unit | >40h - 160h | 3-5 people | >5d - 20d | 21-40 tasks | >$10k - $50k | Requirements are not obvious with potential for misunderstanding | Small Project
| 6-20 deliverables | Department-wide | >160h - 1000h | 6-20 people | >20d - 3 mos. | 41-100 tasks | >$50k - $200k | Requirements are significant with probable changes | Medium Project
| 21-50 deliverables | Multi-department | >1000h - 5000h | 21-40 people | >3 mos. - 12 mos. | 101-200 tasks | >$200k - $500k | Requirements are extensive with volatile environment and guaranteed changes | Large Project
| >50 deliverables | Organization-wide | >5000h | >40 people | >12 mos. | >200 tasks | >$500k | Requirements have not be defined | Very Large Project or Program

## Scalable Approach (hidden)
Scalable Approach | Based on the results of the previous evaluation, apply project management processes at the corresponding level for the scale of the project.
Process | Minor Initiative 1-2 Deliverables Internal Division/Unit <40h effort 1-2 people <=5d duration 1-20 tasks <=$10,000 Requirements are well-understood and reasonably stable | Small Project 3-5 Deliverables Multi-unit 40-<160h effort 3-5 people >5-20d duration 21-40 tasks >$10k - $50k Requirements are not obvious with potential for misunderstanding | Medium Project 6-20 Deliverables Deptartment-wide 160-<1000h effort 6-20 people >20d - 3 mos. 41-100 tasks >$50k - $200k Requirements are significant with probable changes | Large Project 21-50 Deliverables Multi-department 1000-5000h effort 21-40 people >3 mos. - 12 mos. 101-200 tasks >$200k - $500k Requirements are extensive with volatile environment and guaranteed changes | Very Large Project or Program >50 Deliverables Organization-wide >5000h effort >40 people >12 mos. >200 tasks >$500k Requirements have not be defined
Project Initiation/Approval | Email Directive or Request | Basic Charter with Need, Objectives, Product Description, Duration Estimate Range, Cost Estimate Range, PM Authority, Signature | Basic Charter with Need, Objectives, Product Description, Duration Estimate Range, Cost Estimate Range, PM Authority, Signature | Business Case with, Problem/Opportunity, Alternatives, Recommendation; and Full Charter with Need, Objectives, Product Description, Duration Estimate Range, Cost Estimate Range, PM Authority, Signature | Business Case with Problem/Opportunity, Alternatives, Recommendation; and Full Charter with Need, Objectives, Product Description, Duration Estimate Range, Cost Estimate Range, PM Authority, Signature
Deliverable Definition | Basic list of products to be delivered | Basic descriptions of deliverables, possibly broken down into components | Detailed descriptions of deliverables and components with objectively measurable acceptance criteria. Some specifications of deliverables may be defined. | Full, detailed scope statement with deliverable descriptions, detailed specifications for each deliverable and component, objectively measurable acceptance criteria, and scope exclusions. | Full, detailed scope statement with deliverable descriptions, detailed specifications for each deliverable and component, objectively measurable acceptance criteria, and scope exclusions.
Task List | Basic checklist of activities related to deliverables | Prioritized breakdown of large tasks and small activities in a basic project plan table. | Excel work breakdown structure with all tasks organized into summary phases (Basic Plan Template) | Full WBS (possibly in PM software) with 2-3 level breakdown of tasks into work packages and activities | Full WBS (possibly in PM software) with 2-3 level breakdown of tasks into work packages; and WBS Dictionary of activities, instructions and other details associated with work packages.
Resource Assignments | Directly assign personnel to activities (conversation or email) | Assign and estimate people for each task in a basic project plan template. | Assign and estimate effort for people, material and equipment as required for each task and aggregate values to summary phases (Basic Plan Template) | Assign and estimate people, material and equipment as required for each task, possibly in PM software. | Assign and estimate people, material and equipment as required for each task, possibly in PM software.
Schedule | Due dates for tasks on checklist | Expected duration, start and finish dates on tasks in a basic project plan table | Established baseline schedule with durations, start and finish dates in basic project plan table. Basic Excel Gantt chart with baseline plan and expected/actual bars | Detailed project schedule with table, Gantt chart, milestone chart, and baseline schedule, possibly in PM software. | Full, leveled and optimized project schedule with critical path, baseline, deadlines, constraints, and multiple display formats, possibly in PM software.
Budget | Only as necessary | Rough cost estimates assigned to internal resources and tasks | Definitive cost estimates for internal resources and tasks. Basic task and resource expense statements for project. | Definitive cost estimates for internal and external resources and tasks. Detailed and summary task and resource expense statements for project. | Definitive cost baseline with all resource and task costs plus contingency reserve; and Detailed and summary task and resource expense statements, plus cash flow and cost performance baseline.
Risk Planning | Talk about what could go wrong to possibly reduce risks. | Brainstorm common risks that could occur and create a categorized risk list. | Identify risks in a risk listing and perform a qualitative analysis to prioritize the risks based on probability and impact. | Develop a full risk register with risk identification, qualitative analysis and proactive risk response strategies to reduce, transfer or eliminate risks. | Assign a risk manager, Develop a full risk register, Quantify high exposure risks, Review and identify risks regularly throughout the project.
Progress Tracking | Check off and deliver products when complete. | Review tasks bi-weekly to determine tasks complete and remaining tasks. | Review tasks bi-weekly, collect actual and remaining work and duration to determine status and forecast. | Track actual and remaining work on tasks monthly. Determine % work complete, physical % complete, % duration complete. | Track task completion monthly. Apply earned value management to measure status, performance, trends and forecast. Possibly use PM software.
Reporting | Informal notification of completion. | Report when complete. | Report bi-weekly on progress and forecast. | Report monthly on deliverable status, work progress, schedule and budget performance, resource usage, risks/issues, and changes. | Report monthly on deliverable status, work progress, schedule and budget performance using earned value management, resource usage, risks/issues, and changes.
Closing/Termination | Only as necessary | Review and delivery of final product. | Review and formal acceptance of final product with signature. Transfer deliverable and responsibilities for maintenance. | Review and formal acceptance of final product with signature. Transfer deliverable and responsibilities for maintenance. Review lessons learned and initiate improvements. | Review and formal acceptance of final product with signature. Complete full project audit with final report. Transfer deliverable and responsibilities for maintenance. Review lessons learned and initiate improvements.