## Basic Project Plan Template
Basic Project Plan
Project Name:
Client:
Date:
Deliverables & Tasks | Resources | Work (hours) | Duration (days) | Start Date | Finish Date | Deadline Date | Risks
Deliverable Description
Tasks

## Sample Project Schedule
Simple Project Schedule
Project Name: | Widget Development Project Sample
Actual/Expected
Original Plan
Task | 2017-12-03 | 2017-12-10 | 2017-12-17 | 2017-12-24 | 2017-12-31 | 2018-01-07 | 2018-01-14 | 2018-01-21 | 2018-01-28 | 2018-02-04 | 2018-02-11 | 2018-02-18 | 2018-02-25 | 2018-03-04 | 2018-03-11 | 2018-03-18 | 2018-03-25 | 2018-04-01 | 2018-04-08 | 2018-04-15 | 2018-04-22 | 2018-04-29 | 2018-05-06 | 2018-05-13 | 2018-05-20 | 2018-05-27 | 2018-06-03 | 2018-06-10 | 2018-06-17
Project Management
Plan project | bar: 2017-12-03 to 2017-12-24
Control projct | bar: 2017-12-31 to 2018-06-10
Close project | bar: 2018-06-17
Design
Design Module 1 | bar: 2017-12-31 to 2018-01-07
Design Module 2 | bar: 2018-01-14 to 2018-01-28
Design Module 3 | bar: 2018-01-14 to 2018-01-21
Development
Develop Module 1 | bar: 2018-02-04 to 2018-02-25
Develop Module 2 | bar: 2018-02-04 to 2018-03-25
Develop Module 3 | bar: 2018-02-04 to 2018-03-11
Testing
Test Module 1 | bar: 2018-04-01 to 2018-04-15
Test Module 2 | bar: 2018-04-22 to 2018-05-13
Test Module 3 | bar: 2018-05-20 to 2018-06-10